MediGuard AI

Sprint & Roadmap Tracker

90-Day Career Sprint  ·  Week-by-Week Plan  ·  Data Integration  ·  Innovation Timelines

| Field | Detail |
| --- | --- |
| Document type | Sprint & Roadmap Tracker — Living Document |
| Version | v1.0 ¦ March 15, 2026 |
| Author | Ram — Principal Consultant, LTIMindtree |
| Sprint structure | Month 1 = Build ¦ Month 2 = Package ¦ Month 3 = Position |
| Current status | End of Week 2 ¦ Month 1 COMPLETE |
| Audience | Ram (personal reference) ¦ Mentor / accountability partner |

# 1. 90-Day Sprint Overview

| Month | Theme | Goal | Status |
| --- | --- | --- | --- |
| Month 1 Wk 1–4 | BUILD | Core pipeline running, FHIR layer, Gen AI output, zero false positives | ✅ COMPLETE |
| Month 2 Wk 5–8 | PACKAGE | Real data, RAG layer, Streamlit dashboard, evaluation metrics, 4 new ideas | 📋 STARTING |
| Month 3 Wk 9–12 | POSITION | GitHub README, demo video, LinkedIn article, recruiter outreach, LTIMindtree pitch | 📋 PLANNED |

# 2. Week-by-Week Plan

MONTH 1 — BUILD

| Week | Theme / Status | Tasks & Deliverables |
| --- | --- | --- |
| Week 1 Mar 1–7 | Environment & Core Pipeline ✅ DONE | ✅ Python environment, VS Code, GitHub repo setup ✅ fwa_data_pipeline.py — synthetic data generation, rule engine, Isolation Forest ✅ fwa_langchain_reasoning.py — Groq integration, prompt engineering ✅ First real AI narrative output confirmed ✅ Groq TPD limit handling (retry logic, clear error messages) |
| Week 2 Mar 8–15 | FHIR Layer & Full Run ✅ DONE | ✅ fhir_sample_generator.py v3 — 50 EOBs, 4 FWA patterns, POS embedded ✅ fhir_converter.py v2 — three-layer POS resolution, cpt_expected_specialty ✅ fwa_data_pipeline.py — FHIR data source, NCCI -B expansion, data-driven specialty mismatch ✅ Full pipeline run: 15/15 Groq completions, 0 false positives, 87/100 avg risk ✅ Four new innovation ideas documented ✅ Session notes + all four portfolio documents started |
| Week 3 Mar 16–22 | Real Data Integration 📋 NEXT | 📋 CMS SynPUF CSV loader — cms_synpuf_loader.py (column mapper) 📋 CMS BCDA sandbox — DATA_SOURCE = 'cms_bcda' path in pipeline 📋 Download CMS NCCI PTP edits CSV — replace 6 hardcoded NCCI_BUNDLES pairs 📋 Download CMS MUE Excel — replace 7 hardcoded MUE_LIMITS entries 📋 Run UNBUNDLING claims through Groq (MAX_CLAIMS = 34) 📋 Save 3–5 best narratives for LinkedIn article |
| Week 4 Mar 23–29 | Prompt Tuning & Claude vs Groq 📋 PLANNED | 📋 Fix UNBUNDLING + ICD_CPT_MISMATCH category label issue (prompt anchoring) 📋 Compare Claude Opus vs Groq narrative quality on same claims 📋 ICD-10-CM reference file integration (replace ICD_REFERENCE) 📋 Provider benchmark improvements 📋 Week 4 session notes + document updates |

MONTH 2 — PACKAGE

| Week | Theme / Status | Tasks & Deliverables |
| --- | --- | --- |
| Week 5 Mar 30–Apr 5 | Persona-Adaptive Reports + RAG Layer 📋 PLANNED | 📋 Idea 1: Persona-Adaptive Reports — SIU / Compliance / Legal outputs 📋 ChromaDB setup — embed CMS ICD-10-CM, NCCI, MUE as vector store (POS Layer 3) 📋 Streamlit dashboard scaffold — bright enterprise SaaS UI, light background 📋 Dashboard: claims table, risk score distribution, FWA category breakdown |
| Week 6 Apr 6–12 | Streamlit Dashboard + Scheme Narratives 📋 PLANNED | 📋 Idea 2: Scheme-Level Narratives — NetworkX provider graph + Groq scheme writer 📋 Streamlit: AI narrative viewer, SIU referral export, persona toggle 📋 Provider relationship graph visualization in dashboard 📋 CMS SynPUF full dataset run (500K+ claims pipeline test) |
| Week 7 Apr 13–19 | Counter-GenAI + Evaluation Metrics 📋 PLANNED | 📋 Idea 3: Counter-GenAI detection — stylistic anomaly flags on synthetic claims 📋 Evaluation metrics: precision, recall, F1 score, confusion matrix 📋 Benchmark MediGuard AI vs. rule-only baseline 📋 Dashboard: evaluation metrics panel |
| Week 8 Apr 20–26 | GitHub Polish + Demo Video 📋 PLANNED | 📋 GitHub README — architecture diagram, quickstart, sample output screenshots 📋 3–4 minute demo video walkthrough 📋 LinkedIn article draft — final review 📋 LTIMindtree internal POC deck (Month 3 prep) |

MONTH 3 — POSITION

| Week | Theme / Status | Tasks & Deliverables |
| --- | --- | --- |
| Week 9 Apr 27–May 3 | LinkedIn Launch 📋 PLANNED | 📋 Publish LinkedIn article: 'I built an AI FWA detection system in 8 weeks' 📋 LinkedIn milestone posts (weeks 1-4 retrospective) 📋 GitHub repo public launch — share with network 📋 Begin recruiter outreach — Codoxo, Alivia Analytics, GDIT, Healthcare Fraud Shield |
| Week 10 May 4–10 | LTIMindtree Internal Pitch 📋 PLANNED | 📋 Present MediGuard AI POC to LTIMindtree healthcare practice 📋 Identify internal client engagement opportunities 📋 Knowledge Graph prototype (Idea 4) — SNOMED-CT integration start 📋 Senior/Director role applications — target 5 per week |
| Week 11 May 11–17 | Recruiter Engagement 📋 PLANNED | 📋 Interview preparation — technical deep-dives using Doc 1 📋 Domain storytelling using Doc 2 positioning statements 📋 Follow-up on applications + LinkedIn outreach responses 📋 Knowledge Graph — clinical coherence demo ready |
| Week 12 May 18–24 | Sprint Close & Retrospective 📋 PLANNED | 📋 Sprint retrospective — what worked, what to continue 📋 All four documents updated to final versions 📋 90-day retrospective LinkedIn post 📋 Evaluate full-time vs. consulting engagement pathway based on responses |

# 3. Data Integration Plan

MediGuard AI evolves through three data maturity phases. Each phase increases realism and credibility without requiring a BAA or proprietary data access until Phase 3.

## 3.1  Phase 1 — Synthetic FHIR (Current — Complete)

| Component | Current State | Notes |
| --- | --- | --- |
| Claims source | fhir_sample_generator.py — 50 synthetic EOBs | ✅ Working |
| CPT reference | 20 hardcoded codes in CPT_REFERENCE dict | ✅ Sufficient for POC |
| ICD reference | 18 hardcoded codes in ICD_REFERENCE dict | ✅ Sufficient for POC |
| NCCI rules | 6 hardcoded pairs in NCCI_BUNDLES list | ✅ Sufficient for POC |
| MUE limits | 7 hardcoded CPTs in MUE_LIMITS dict | ✅ Sufficient for POC |
| POS resolution | 3-layer: FHIR → CPT range → RAG(roadmap) | ✅ Layers 1+2 active |
| Specialty check | FHIR extension cpt_expected_specialty | ✅ Data-driven, scalable |

## 3.2  Phase 2 — Real CMS Public Data (Month 2)

| Data Source | What It Replaces | Download Location | Format | Timeline |
| --- | --- | --- | --- | --- |
| CMS SynPUF CSV | Our 50 synthetic claims | data.cms.gov/medicare-claims-synthetic-public-use-files | Flat CSV | Week 3 |
| CMS BCDA Sandbox | fhir_sample_generator.py | sandbox.bcda.cms.gov/api/v2/ExplanationOfBenefit | FHIR R4 API | Week 3 |
| CMS NCCI PTP Edits | 6 hardcoded NCCI_BUNDLES | cms.gov/medicare/coding-billing/national-correct-coding | CSV | Week 3 |
| CMS MUE Table | 7 hardcoded MUE_LIMITS | cms.gov/medicare/coding-billing/mue | Excel | Week 3 |
| CMS ICD-10-CM Tabular | 18 hardcoded ICD_REFERENCE | cms.gov/medicare/coding/icd10 | XML/CSV | Week 4 |
| CMS Physician Fee Sched | 20 hardcoded CPT_REFERENCE | cms.gov/medicare/physician-fee-schedule | CSV | Week 4 |

All Phase 2 sources are: free to download, publicly available, no registration required, no BAA required, and officially published by CMS. This eliminates all hardcoded reference data from the pipeline.

## 3.3  Phase 3 — Real Masked Claims (Month 3)

Phase 3 — The Client Conversation

What it requires: A Business Associate Agreement (BAA) with a payer or health plan. What it enables: Running MediGuard AI against actual de-identified Medicare/Medicaid claims. This is not a technology gap — the pipeline is already built and FHIR-compliant. Phase 3 is a business development conversation, not an engineering task. Target engagement scenarios: • LTIMindtree payer client engagement — present MediGuard AI as a proof-of-concept • Direct outreach to Codoxo, Alivia Analytics, GDIT — offer to run against their test data • Healthcare AI hiring — 'I can run this against your claims data in Week 1' The pitch: The architecture is already built. Point it at your FHIR endpoint and we go live.

# 4. Innovation Ideas — Implementation Timelines

## Idea 1 — Persona-Adaptive Reports

| Task | Week | Dependency | Effort |
| --- | --- | --- | --- |
| Design three prompt schemas (SIU / Compliance / Legal) | Week 5 | Existing Groq integration | 2 hours |
| Add persona parameter to fwa_langchain_reasoning.py | Week 5 | Above | 1 hour |
| Add persona toggle to Streamlit dashboard | Week 5 | Streamlit scaffold | 2 hours |
| Test all three outputs on 5 sample claims | Week 5 | Above | 1 hour |
| Document in Technical Reference | Week 5 | Completion | 30 min |

## Idea 2 — Scheme-Level Narratives

| Task | Week | Dependency | Effort |
| --- | --- | --- | --- |
| Build NetworkX provider relationship graph from scored claims | Week 6 | fwa_scored_claims.csv | 4 hours |
| Define scheme detection thresholds (min claims, time window) | Week 6 | Above | 2 hours |
| Write Groq scheme narrative prompt (graph → narrative) | Week 6 | Above | 2 hours |
| Add scheme view to Streamlit dashboard | Week 6 | Streamlit + NetworkX | 3 hours |
| Test on synthetic data — inject multi-provider fraud ring | Week 6 | Above | 2 hours |

## Idea 3 — Counter-GenAI Detection

| Task | Week | Dependency | Effort |
| --- | --- | --- | --- |
| Define AI-fraud detection signals (variance, round numbers, etc) | Week 7 | Domain research | 3 hours |
| Build anomaly scorer for claim pattern variance | Week 7 | fwa_data_pipeline.py | 4 hours |
| Add AI-fraud flag to rule engine output | Week 7 | Above | 2 hours |
| Groq prompt addition: explain AI-generation suspicion | Week 7 | Existing Groq layer | 2 hours |
| Test: generate 'too perfect' synthetic claims, run through system | Week 7 | Above | 3 hours |
| LinkedIn angle: 'AI catches AI fraud' post | Week 9 | Completion | 1 hour |

## Idea 4 — Medical Knowledge Graph

| Task | Week | Dependency | Effort |
| --- | --- | --- | --- |
| Research SNOMED-CT and RxNorm APIs — identify free tiers | Week 10 | — | 2 hours |
| Build lightweight clinical coherence checker (age + dx + proc) | Week 10 | SNOMED-CT | 6 hours |
| Integrate coherence check into rule engine as Layer 3.5 | Week 11 | Above | 3 hours |
| Groq prompt: include clinical coherence context | Week 11 | Above | 2 hours |
| Test: inject age-inappropriate + diagnosis-inconsistent claims | Week 11 | Above | 3 hours |
| Document as published-gap differentiator in all four docs | Week 11 | Completion | 1 hour |

# 5. Pending Items & Known Issues

## 5.1  Immediate (Week 3)

| Item | Issue | Fix Approach | Priority |
| --- | --- | --- | --- |
| UNBUNDLING category label | Groq labels UNBUNDLING as MEDICALLY_UNNECESSARY | Strengthen ★ CONFIRMED FRAUD PATTERN override in system prompt | HIGH |
| ICD_CPT_MISMATCH label | Groq labels MISMATCH as MEDICALLY_UNNECESSARY | Same prompt fix — directive override not advisory | HIGH |
| MAX_CLAIMS setting | Currently 20 — misses UNBUNDLING claims (pos 16+) | Set MAX_CLAIMS_TO_ANALYZE = 34 for full run | MEDIUM |
| CMS NCCI download | Currently 6 hardcoded pairs | Download from cms.gov — drop-in replacement | MEDIUM |
| CMS MUE download | Currently 7 hardcoded CPTs | Download Excel from cms.gov — drop-in replacement | MEDIUM |

## 5.2  Month 2 Backlog

| Item | Description | Week Target |
| --- | --- | --- |
| ChromaDB RAG layer | POS Layer 3 — embed full CMS POS-CPT reference table | Week 5 |
| Streamlit dashboard | Bright enterprise SaaS UI — not dark terminal style | Week 5-6 |
| Evaluation metrics | Precision, recall, F1, confusion matrix vs. rule-only baseline | Week 7 |
| Patient demographics | FHIR EOB doesn't carry demographics — fetch Patient resource from BCDA API | Week 6 |
| CMS BCDA live integration | DATA_SOURCE = 'cms_bcda' — currently placeholder comment in fhir_converter.py | Week 3 |
| Knowledge Graph prototype | SNOMED-CT + RxNorm clinical coherence layer (Idea 4) | Week 10 |

## 5.3  Architecture Decisions Still Open

| Decision | Options | Current Leaning | Decide By |
| --- | --- | --- | --- |
| ChromaDB vs. Pinecone for RAG | ChromaDB (local, free) vs. Pinecone (cloud, paid) | ChromaDB — keeps POC fully local and free | Week 5 |
| Streamlit vs. Gradio for UI | Streamlit (full dashboard) vs. Gradio (quick demo) | Streamlit — richer UI for portfolio demo | Week 5 |
| Claude vs. Groq for narratives | Compare quality on same 15 claims | Run comparison Week 4 — decide based on quality+cost | Week 4 |
| Graph DB vs. NetworkX | NetworkX (lightweight) vs. Neo4j (production-grade) | NetworkX for POC — mentions Neo4j in architecture story | Week 6 |

# 6. Calendar Reminders & Key Dates

| Date | Event | Notes |
| --- | --- | --- |
| March 16, 2026 | Week 3 sprint start | CMS data downloads + BCDA sandbox integration |
| March 23, 2026 | Week 4 sprint start | Prompt tuning + Claude vs Groq comparison |
| March 30, 2026 | Month 2 start — PACKAGE phase | Streamlit + RAG + Persona-Adaptive Reports |
| April 10, 2026 | MediGuard AI V2 — Design RAG Layer | Existing calendar reminder set (Event ID: 1456) |
| April 26, 2026 | Month 2 close — all packaging done | GitHub README, demo video, LinkedIn draft |
| April 27, 2026 | Month 3 start — POSITION phase | LinkedIn publish, recruiter outreach begins |
| May 24, 2026 | 90-day sprint close | Retrospective, final doc updates |

MediGuard AI  |  Sprint & Roadmap Tracker v1.0  |  March 15, 2026  |  LIVING DOCUMENT